## 08-junio
Sprint Planning and Task Division between Team Members
Name | Description | Group Tasks | Team Tasks
Nicole García | Assined as a member of frontend team Start working on new-task-form-component | Front: Using Clean Arquitecture to define the front-end structure of the project. | Make the diagram for the database schema of CRONUS project
Doménica Barreiro | SCRUM master, meeting to plan all the sprints for the project Member of front-end team Start working on monthly-view component of calendar page
Camilo Gutiérrez | Created frontend initial structure, adds development dependencies. Start working on orders list view.
Nicole Agila | Creating models for the objects: Event - Event type - Task - Task Type - Maintenance - Priority - Repair | Back: Defining the back-end structure of project with Django.
Sebastián Benalcázar | Creating models for the objects: Branch office - Machine - Employee - Machine type - User
David Cevallos | Learning Django (He joined the team recently and did not know the frameworks and languages we used)

## 12-junio
Meeting with client and Refactoring of Low-Fi prototype
Name | Description | Group Tasks
Nicole García | Working on create-new-task-form component | Front: Meeting to discuss abour the best type of views to show the orders
Doménica Barreiro | Working on monthly-view component
Camilo Gutiérrez | Updates the prototype, adds orders list table, and events view header
Nicole Agila | Working on events and workflow GET endpoints. Redefine the database model adding new tables that make up templates and workflow steps. | Back: Meeting to redefine the database model based on new requirements
Sebastián Benalcázar | Working on events POST endpoints, Branchoffice and available hours get endpoints.
David Cevallos | Learning the definitions of migrations, views, templates, ORM and querysets

## 14-junio
New Prototype Review and Working on Changed Requirements
Name | Description
Nicole García | Working on show-order-detail component Refactoring the create-new-order-component Using dummy data to the components
Doménica Barreiro | Review of prototype and new views of application Start working on weekly-view component for calendar view
Camilo Gutiérrez | Creates events handler to see orders in a day and events handler to create orders.
Nicole Agila | Adapt and implement new GET endpoints to deliver information based on front views needs.
Sebastián Benalcázar | Adapt and implement new POST endpoint for Orders. Adapt the response to retrieve the 3 objects that POST create
David Cevallos | Create the view for the user authentication and login.

## 21-junio
Final tasks and Deployment of Application for the Demo with the Client
Name | Description
Nicole García | Using the endpoint to get workflows and available schedules in create-a-new-task component Using the endpoint to get information about a specific task in show-task-detail component Fix the status colors in both components
Doménica Barreiro | Finish the weekly-view component and add to calendar page with all funcitonalities Using the endpoint to get all tasks for a week time in weekly-view component
Camilo Gutiérrez | Adds configuration files on the backend to serves the frontend build from the backend service.
Nicole Agila | Modifying the events and workflows GET endpoints to fulfill the new requirements.
Sebastián Benalcázar | Modifying the orders endpoint to fullfill the new requierments and reducing the amount of params that the front-end teams needs to send in the body of the post
David Cevallos | Modify the admin of django to a better display in the admin page.

## 25-junio
Task distribution to complete the Partial Project Report
Name | Description
Nicole García | Adding webpack and ESLINT to the fronted. Correcting and generate reports before use the linters. Having a meeting with Domenica to organize the daily scrum evidence excel.
Doménica Barreiro | Make Sprint Review template. Review meeting recordings with client to get the new requirements for future iterations. Update Backlog and Sprint 1 status with Camilo and Sebastián. Make the deploy Dockerfile for the project with Camilo.
Camilo Gutiérrez | Documents the new requirements, creates video script, merge the frontend and backend source code in the repository, investigate how to create the dockerfile for the project, updates backlog and sprint.
Nicole Agila | Documentation of user stories from the latest customer demo. Learn how to use black and flake8 in the backend for code analysis.
Sebastián Benalcázar | Documentation of user stories from the latest customer demo. Learn how to use black and flake8 in the backend for code analysis. Edit the video
David Cevallos | Learn how to use black and flake8 in the backend for code analysis. Edit the code.

## 12-julio
Client Feedback review and Fixes of Calendar Module
Name | Description
Nicole García | Changing pieces number input by range selector Fix pieces number function test.
Doménica Barreiro | Add client name and invoice number in calendar view Add time duration of task in calendar view
Camilo Gutiérrez | Start working on mobile application
Nicole Agila | Add new endpoint to get machines by branch office
Sebastián Benalcázar | Add new endpoint to get pieces number ranges
David Cevallos | Add new endpoint to get role user

## 27-julio
Finishing Calendar Module fixes and improvements
Name | Description
Nicole García | Replace workflows by machine selector in create order page
Doménica Barreiro | Add services selector to calendar view
Camilo Gutiérrez | Allow update end date when is a cut task
Nicole Agila | Change the databse to mysql
Sebastián Benalcázar | Change all date to mysql format
David Cevallos | Add new endpoint to update events with security

## 4-agosto
Report Module prototyping, validation and start of development
Name | Description
Nicole García | Protipying report pages Adding report page header
Doménica Barreiro | Protipying report pages Adding filter to page reports
Camilo Gutiérrez | Protipying report pages Adding table compoent to report page
Nicole Agila | Creating report endpoint by branches,
Sebastián Benalcázar | Creating report endpoint for all branches
David Cevallos | Creating admin view with django

## 12-agosto
Finishing Report and Administration modules. Backend endpoints for mobile application.
Name | Description
Nicole García | Adding slideOver component
Doménica Barreiro | Adding Header componets to all pages
Camilo Gutiérrez | Manage when machine change its state in mobile app
Nicole Agila | Adding backend endpoints to mobile app
Sebastián Benalcázar | Fixing file upload when create order
David Cevallos | Working on login/logoaut functions

## 22-agosto
Mobile application development. Peer to peer code review and Refactoring.
Name | Description
Nicole García | Review Domenica's Code Implementing CI pipelines
Doménica Barreiro | Review Camilo's Code Fix react Router
Camilo Gutiérrez | Review Sebastian's Code Working on acceptance testing
Nicole Agila | Review David's Code Working on acceptance testing
Sebastián Benalcázar | Review Nicole's Code Add backend env variables
David Cevallos | Review Nicole's Code Mange roles in backend

## 25-agosto
Task distribution to complete the Final Project Report
Name | Description
Nicole García | Explain the CI pipeline in the document
Doménica Barreiro | Writting scrum section in the documment
Camilo Gutiérrez | Explain architectural decisions
Nicole Agila | Add acceptance test in the document
Sebastián Benalcázar | Write video script
David Cevallos | Writting about the backend and frontend tools and coding standarts