## 08-junio
Sprint Planning and Task Division between Team Members
Name | Description | Group Tasks | Team Tasks
Nicole García | Assined as a member of frontend team Start working on new-task-form-component | Front: Using Clean Arquitecture to define the front-end structure of the project. | Make the diagram for the database schema of CRONUS project
Doménica Barreiro | SCRUM master, meeting to plan all the sprints for the project Member of front-end team Start working on monthly-view component of calendar page
Camilo Gutiérrez | Created frontend initial structure, adds development dependencies. Start working on orders list view.
Nicole Agila | Creating models for the objects: Event - Event type - Task - Task Type - Maintenance - Priority - Repair | Back: Defining the back-end structure of project with Django.
Sebastián Benalcázar | Creating models for the objects: Branch office - Machine - Employee - Machine type - User
David Cevallos | Learning Django (He joined the team recently and did not know the frameworks and languages we used)

## 12-junio
Meeting with client and Refactoring of Low-Fi prototype
Name | Description | Group Tasks
Nicole García | Working on create-new-task-form component | Front: Meeting to discuss abour the best type of views to show the orders
Doménica Barreiro | Working on monthly-view component
Camilo Gutiérrez | Updates the prototype, adds orders list table, and events view header
Nicole Agila | Working on events and workflow GET endpoints. Redefine the database model adding new tables that make up templates and workflow steps. | Back: Meeting to redefine the database model based on new requirements
Sebastián Benalcázar | Working on events POST endpoints, Branchoffice and available hours get endpoints.
David Cevallos | Learning the definitions of migrations, views, templates, ORM and querysets

## 14-junio
New Prototype Review and Working on Changed Requirements
Name | Description
Nicole García | Working on show-order-detail component Refactoring the create-new-order-component Using dummy data to the components
Doménica Barreiro | Review of prototype and new views of application Start working on weekly-view component for calendar view
Camilo Gutiérrez | Creates events handler to see orders in a day and events handler to create orders.
Nicole Agila | Adapt and implement new GET endpoints to deliver information based on front views needs.
Sebastián Benalcázar | Adapt and implement new POST endpoint for Orders. Adapt the response to retrieve the 3 objects that POST create
David Cevallos | Create the view for the user authentication and login.

## 21-junio
Final tasks and Deployment of Application for the Demo with the Client
Name | Description
Nicole García | Using the endpoint to get workflows and available schedules in create-a-new-task component Using the endpoint to get information about a specific task in show-task-detail component Fix the status colors in both components
Doménica Barreiro | Finish the weekly-view component and add to calendar page with all funcitonalities Using the endpoint to get all tasks for a week time in weekly-view component
Camilo Gutiérrez | Adds configuration files on the backend to serves the frontend build from the backend service.
Nicole Agila | Modifying the events and workflows GET endpoints to fulfill the new requirements.
Sebastián Benalcázar | Modifying the orders endpoint to fullfill the new requierments and reducing the amount of params that the front-end teams needs to send in the body of the post
David Cevallos | Modify the admin of django to a better display in the admin page.

## 25-junio
Task distribution to complete the Partial Project Report
Name | Description
Nicole García | Adding webpack and ESLINT to the fronted. Correcting and generate reports before use the linters. Having a meeting with Domenica to organize the daily scrum evidence excel.
Doménica Barreiro | Make Sprint Review template. Review meeting recordings with client to get the new requirements for future iterations. Update Backlog and Sprint 1 status with Camilo and Sebastián. Make the deploy Dockerfile for the project with Camilo.
Camilo Gutiérrez | Documents the new requirements, creates video script, merge the frontend and backend source code in the repository, investigate how to create the dockerfile for the project, updates backlog and sprint.
Nicole Agila | Documentation of user stories from the latest customer demo. Learn how to use black and flake8 in the backend for code analysis.
Sebastián Benalcázar | Documentation of user stories from the latest customer demo. Learn how to use black and flake8 in the backend for code analysis. Edit the video
David Cevallos | Learn how to use black and flake8 in the backend for code analysis. Edit the code.